## Sheet1
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 | 84.5 | 84.5
Code | not started | 2015-01-20 |  |  | 2015-02-25 | 2015-07-01 |  | 47 |  | 40
Test | not started | 2015-03-05 |  |  | 2015-03-25 | 2015-07-29 |  | 20
Total Hours | [7 empty] | 189 | 208 | 178
Accomplishments |  | Started to have a lot of fun coding the project. Have entered multiple objects, and been able to set focus on each one.
Problems |  | rendering movement based on a focus point can be coplicated.
Changes in Scope, Schedule and Cost |  | Behind Schedule |  | Finished the basics for the skybox, but have been having trouble with movement.
Confessional |  | Actual hours since last update: 8.5 hours
Total Anticipated actual Hours: 208
Redoing my schedule this week to compensate.
Scripture |  | Alma 42:29 - ...and only let your [bugs] trouble you, with that trouble which shall bring you down unto [fix them].

## Sheet2
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 | 84.5 | 84.5
Code | not started | 2015-01-20 |  |  | 2015-02-25 | 2015-07-01 |  | 47 |  | 57
Test | not started | 2015-03-05 |  |  | 2015-03-25 | 2015-07-29 |  | 20
Total Hours | [7 empty] | 189 | 258 | 195
Accomplishments |  | Not much … stuck on rotations still.
Problems |  | rendering movement based on a focus point can be coplicated.
Changes in Scope, Schedule and Cost |  | Behind Schedule |  | Changed my focus at the moment to the models between research, so that I can progress
Confessional |  | Actual hours since last update: 17 hours
Total Anticipated actual Hours: 258
Trying to figure out this bug with rotational movement, while moving on to the actual struture of the models.
Scripture |  | Acts 27:41 - And falling into a place where [problems] met, they ran the [project] aground; and the forepart stuck fast, and remained unmoveable, but the hinder part was broken with the violence of the waves.

## Sheet3
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 | 86.5 | 86.5
Code | not started | 2015-01-20 |  |  | 2015-02-25 | 2015-07-01 |  | 47 | 60 | 60
Test | not started | 2015-03-05 |  |  | 2015-03-25 | 2015-07-29 |  | 20
Total Hours | [7 empty] | 189 | 258 | 200
Accomplishments |  | Started making the tank objects, and put a little research time into obj files.
Problems |  | still hammering through making models and looking a bit at rotations.
Changes in Scope, Schedule and Cost |  | Behind Schedule |  | Research a bit about obj files, and decided that is not the way to go, and it would just complicate thing a bit more.
Confessional |  | Actual hours since last update: 5 hours
Total Anticipated actual Hours: 258
Trying to figure out this bug with rotational movement, while moving on to the actual struture of the models.
Scripture |  | Numbers 22:24 - But the [rotational problem]stood in a path of the [James' goal] a wall being on this side, and a wall on that side.