## Sheet1
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 | 84.5 | 84.5
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47 |  | 40
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 208 | 178
Accomplishments |  | Started to have a lot of fun coding the project. Have entered multiple objects, and been able to set focus on each one.
Problems |  | rendering movement based on a focus point can be coplicated.
Changes in Scope, Schedule and Cost |  | Behind Schedule |  | Finished the basics for the skybox, but have been having trouble with movement.
Confessional |  | Actual hours since last update: 8.5 hours
Total Anticipated actual Hours: 208
Redoing my schedule this week to compensate.
Scripture |  | Alma 42:29 - ...and only let your [bugs] trouble you, with that trouble which shall bring you down unto [fix them].