## Status Update 1
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | in progress | 2014-03-01 |  | 2014-03-01 | 2014-05-06 |  |  | 5 hours
Prelim | not started
Proposal | not started
Research | not started
Design | not started
Code | not started
Test | not started
Total Hours
Accomplishments |  | I started moving from Rigby to Rexburg
Problems |  | I started moving from Rigby to Rexburg
Changes in Scope, Schedule and Cost |  |  |  | none thusfar
Confessional |  | Actual hours since last update: 0
Total Anticipated actual Hours: At least 156 hours
I'm going to do my proposal soon
Scripture |  | Abraham 1:1: ...I, [James], saw that it was needful for me to obtain another place of residence;

## Status Update 2
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | in progress | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 hours |  | 6 hours
Prelim | in progress | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 |  | 3 hours
Proposal | in progress | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 |  | 4 hours
Research | not started
Design | not started
Code | not started
Test | not started
Total Hours
Accomplishments |  | I finished moving from Rigby to Rexburg, I have finally decided on my project and have half of my proposal done
Problems |  | I finished moving from Rigby to Rexburg
Changes in Scope, Schedule and Cost |  |  |  | none thusfar
Confessional |  | Actual hours since last update: 3 hours
Total Anticipated actual Hours: At least 156 hours
I'm currently doing my proposal
Scripture |  | Nehemiah 5:8: …Then held [James] his peace, and found nothing to [research].

## Status Update 3
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | in progress | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 |  |  | 60
Research/ Design | not started | 2014-07-25 |  |  | 2014-07-25 |  |  | 50
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 |  | 13
Accomplishments |  | I finished my proposal, and have received an approval from Br. Twitchell.
Problems |  | Time waits for no individual.
Changes in Scope, Schedule and Cost |  | Behind Schedule |  | I am behind by a day in my research because homework piles up during the week. I will have to change my current plan to work on Saturdays to compensate for other classes.
Confessional |  | Actual hours since last update: 7 hours
Total Anticipated actual Hours: 189
Have finished my proposal and research will be started today.
Scripture |  | 2 Corinthians 6:4: But in all things approving ourselves as [owners of the project], in much patience, in afflictions, in necessities, in distresses,…

## Status Update 4
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | in progress | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 |  |  | 60 |  | 3.5
Research/ Design | not started | 2014-07-25 |  |  | 2014-07-25 |  |  | 50
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 |  | 16.5
Accomplishments |  | I understand a bit more mow the capabilities of SDL and the installation of it.
Problems |  | Spent a bit of time with my family. Spent too much time at the plasma center yesterday.
Changes in Scope, Schedule and Cost |  | Behind Schedule |  | I am behind schedule on research, but am planning to make it up on Friday and Saturday.
Confessional |  | Actual hours since last update: 3.5 hours
Total Anticipated actual Hours: 189
Research has been started, and I am learning a bit about the capabilities of SDL.
Scripture |  | 1 Corinthians = And this I speak for your own [project]; not that I may cast [more homework] upon you, but for that which is comely, and that ye may attend upon the [project] without distraction.

## status update 5
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | in progress | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 |  |  | 60 |  | 6
Research/ Design | not started | 2014-07-25 |  |  | 2014-07-25 |  |  | 50
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 |  | 19
Accomplishments |  | I understand a bit more mow the capabilities of SDL and the installation of it.
Problems |  | Homework is piling up in other classes as well as this one.
Changes in Scope, Schedule and Cost |  | Behind Schedule |  | I am behind schedule on research, but am planning to make it up on Friday and Saturday.
Confessional |  | Actual hours since last update: 2.5 hours
Total Anticipated actual Hours: 189
Research has been started, and I am learning a bit about the capabilities of SDL.
Scripture |  | 1 Corinthians = And this I speak for your own [project]; not that I may cast [more homework] upon you, but for that which is comely, and that ye may attend upon the [project] without distraction.

## status update 6
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | in progress | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 |  |  | 60 |  | 15
Research/ Design | not started | 2014-07-25 |  |  | 2014-07-25 |  |  | 50
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 |  | 28
Accomplishments |  | I dropped Math 330 in order to have more time for senior project. I discovered that I am going to have to use Windows because of drivers developed for Windows.
Problems |  | I discovered that I am going to have to use Windows because of drivers developed for Windows.
Changes in Scope, Schedule and Cost |  | Behind Schedule |  | I am behind schedule on research, but have been able to start catching up because of increased time.
Confessional |  | Actual hours since last update: 9 hours
Total Anticipated actual Hours: 189
Research has been started, and I am learning a bit about the correlation between SDL Windows and openGL.
Scripture |  | Alma 60: 30 = …and I [drop Math 330 without regret], insomuch that [it] can have no more power to impede the progress of this [project] in the cause of my [graduation].

## Status Update 7
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | in progress | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-06-26 |  | 60 |  | 23.5
Research/ Design | not started | 2014-07-25 |  |  | 2014-07-25 |  |  | 50
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 190 | 36.5
Accomplishments |  | I discovered something that surprised me. The in openGL the camera does not move, rather the whole scene does. Made some decisions on the tanks I will use. Starting to enjoy my research a little bit. Started estimating my hours with a better method.
Problems |  | Had to adjust my schedule.
Changes in Scope, Schedule and Cost |  | Behind Schedule |  | Backed my requirements due date off by a week.
Confessional |  | Actual hours since last update: 8.5 hours
Total Anticipated actual Hours: 190
Learned more about the camera and started deciding on tanks.
Scripture |  | JSH 1:21 = Some few days after I had this vision, I happened to be in company with one of the Methodist preachers, who was very active in the before mentioned religious excitement; and, conversing with him on the subject of religion, I took occasion to give him an account of the vision which I had had. I was greatly surprised at his behavior; he treated my communication not only lightly, but with great contempt, saying it was all of the devil, that there were no such things as visions or revelations in these days; that all such things had ceased with the apostles, and that there would never be any more of them.

## Status Update 8
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | in progress | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-06-26 |  | 60 |  | 26
Research/ Design | not started | 2014-07-25 |  |  | 2014-07-25 |  |  | 50
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 190 | 39
Accomplishments |  | Have housing set up for my internship this fall. Started researching more of what matrices do, and thinking about adding a skybox or skydome to my requirements.
Problems |  | Needed to help my pregnant wife with the kids more this week. My daughter sprained her elbow. Spent a lot of time on the phone with an apartment complex in Utah for my internship.
Changes in Scope, Schedule and Cost |  | Behind Schedule |  | Backed my requirements due date off by a week.
Confessional |  | Actual hours since last update: 2.5 hours
Total Anticipated actual Hours: 190
Started researching more of what matrices do, and thinking about adding a skybox or skydome to my requirements.
Scripture |  | Psalms 119 : 60 = I [wish] made haste, and delayed not to [finish my requirements].

## Status Update 9
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | in progress | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 |  | 60 |  | 32.5
Research/ Design | not started | 2014-07-25 |  |  | 2014-07-25 |  |  | 50
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 190 | 45.5
Accomplishments |  | Have realized that I have a problem with wording my requirements, and am still trying to make sure they explicitely say what I mean. Learned more about shadow mapping, and skyboxes.
Problems |  | Have realized that I have a problem with wording my requirements, and am still trying to make sure they explicitely say what I mean.
Changes in Scope, Schedule and Cost |  | Behind Schedule |  | Backed my requirements due date off by a week.
Confessional |  | Actual hours since last update: 6.5 hours
Total Anticipated actual Hours: 190
Learned more about shadow mapping and skyboxes.
Scripture |  | Mormon 9:34 = "But the Lord knoweth the things which we have written, and also that none other people knoweth our language; and because that none other people knoweth our language, therefore he hath prepared means for the interpretation thereof." (I wish I had help like this for my requirements.)

## Status Update 10
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | in progress | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 |  | 60 |  | 36.5
Research/ Design | not started | 2014-07-25 |  |  | 2014-07-25 |  |  | 50
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 190 | 49.5
Accomplishments |  | Went on a trip to see my wive's great great grandma for her 100th birthday and still got some work done. Hoping still to turn in my requirements today.
Problems |  | Didn't get as much as I wanted to done.
Changes in Scope, Schedule and Cost |  | Behind Schedule |  | Backed my requirements due date off by a week.
Confessional |  | Actual hours since last update: 4 hours
Total Anticipated actual Hours: 190
Almost funished my requirements, realized I have a few more to put in there because I missed some with my thinking.
Scripture |  | 1 Nephi 3:5 = And now, behold [I should not] murmur, saying it is a hard thing which [Twitchell has] required of [me]; but behold [Twitchell has] not required it of me, but it is a commandment of [myself].

## Status Update 11
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 177.5 | 53.5
Accomplishments |  | My requirements were approved.
Problems |  | Didn't get as much as I wanted to done over 4th of July weekend.My requirements were approved.
Changes in Scope, Schedule and Cost |  | Behind Schedule |  | Backed of research/design to 9/25/2014.
Confessional |  | Actual hours since last update: 4 hours
Total Anticipated actual Hours: 177.5
Finished my requirements. Move research/design back to 9/25/2014.
Scripture |  | Romans 8:29 For [my requirements which I] did foreknow, [I] also did predestinate [senior project] to be conformed to [my own requirements], that [I] might [graduate] among many brethren.

## Status Update 12
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 |  | 22.5
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 177.5 | 76
Accomplishments |  | I shipped my family off to Utah for the weekend so I can finish up my hours.
Problems |  | I have 21 hours left so I need to average 7 hours a day. I hit that point where the problem becomes bigger than I origionally thought. Won't even be able to see a simple graphic until I get a lot of the math done (MVP matrrices, etc.).
Changes in Scope, Schedule and Cost |  | On Schedule |  | Backed of research/design to 9/25/2014.
Confessional |  | Actual hours since last update: 22.5 hours
Total Anticipated actual Hours: 177.5
Still working on research and design, looking to understand MVP and matrices at the moment.
Scripture |  | 29 And in [the day that the matrices are done] shall the deaf [program wait for sound effects], and the eyes of the blind [project] shall see out of obscurity and out of darkness.

## Status Update 13
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 |  | 32.5
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 177.5 | 86
Accomplishments |  | Still realizing how much work I have to do to understand the rest of my project especially MVP.
Problems |  | Still realizing how much work I have to do to understand the rest of my project especially MVP.
Changes in Scope, Schedule and Cost |  | On Schedule |  | Backed of research/design to 9/25/2014.
Confessional |  | Actual hours since last update: 10 hours
Total Anticipated actual Hours: 177.5
Still working on research and design, looking to understand MVP and matrices at the moment.
Scripture |  | 1 Nephi 15:3 For [I] truly spake [learned the start of] great things, which were hard to be understood, save a man should inquire of the Lord...

## Status Update 14
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 |  | 32.5
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 177.5 | 86
Accomplishments |  | Finished an internship successfully.
Problems |  | When I got the resources I needed, My schedule became busy all of the sudden.
Changes in Scope, Schedule and Cost |  | Behind Schedule |  | Need to work on this project more.
Confessional |  | Actual hours since last update: 0 hours
Total Anticipated actual Hours: 177.5
Will be changing schedule this week and starting on matrices.
Scripture |  | Daniel 7:12 - … yet [James' Senior Project was] prolonged for a time and a season.

## Status update 15
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 |  | 36.5
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 177.5 | 90
Accomplishments |  | found driver updates and Opengl benchmark tests. Researched more on how to design my matrices.
Problems |  | Still trying to wrap my head around the matrices and how they will be the base for my programmable pipeline.
Changes in Scope, Schedule and Cost |  | On Schedule |  | I have adjusted my dates so that I am now on schedule, but it will be easy to get behind.
Confessional |  | Actual hours since last update: 4 hours
Total Anticipated actual Hours: 177.5
get an idea of where I'm headed with the matrices and start programming them.
Scripture |  | Isaiah 34:11 - ...and [James] shall stretch out upon the line of confusion, and the stones of emptiness.

## Status Update 16
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 |  | 43.5
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 177.5 | 97
Accomplishments |  | Recovered from a hard drive wipe. Set up a linux environment for coding opengl with sdl2 and c++. More research on matrices and opengl for design.
Problems |  | Accidentally wiped my hard drive while messing with partitions.
Changes in Scope, Schedule and Cost |  | On Schedule |  | currently on schedule but will need to finish my matrices soon.
Confessional |  | Actual hours since last update: 7 hours
Total Anticipated actual Hours: 177.5
Understand more about matrices and code the backend with matrices.
Scripture |  | Moses 16:4 - Thus all [the hard drive files] were lost; and behold, they would have been endlessly lost were it not that [James] redeemed [some of] his [assignments] from their lost and fallen state.

## Status Update 17
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 |  | 45.5
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 177.5 | 99
Accomplishments |  | Got caught up on all my other homework.
Problems |  | Got behind on other homework, and it of course affected this.
Changes in Scope, Schedule and Cost |  | Behind Schedule |  | Will need to finish matrices this week.
Confessional |  | Actual hours since last update: 2 hours
Total Anticipated actual Hours: 177.5
Code the backend with matrices.
Scripture |  | Joshua 8:4 - And [teachers] commanded [homework assignments], saying, Behold, ye shall lie in wait against the [students], even behind [them]: go not very far from the [students], but be ye all ready:

## Status Update 18
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 |  | 54
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47 |  | 2
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 177.5 | 109.5
Accomplishments |  | changed my renderer to webgl from SDL2 (with the approval of Br. Twitchell).
Problems |  | I feel like I wasted too much time on the previous renderer
Changes in Scope, Schedule and Cost |  | Behind Schedule |  | Learning more about opengl now the the framework is working correctly
Confessional |  | Actual hours since last update: 10.5 hours
Total Anticipated actual Hours: 177.5
Learning more about opengl now the the framework is working correctly
Scripture |  | Philippians 1:10 - That [Br. Twitchell] may approve things that are excellent [a.k.a. webgl]; that [Br. Twitchell] may be sincere and without offence till the day of [the deadline];

## Status Update 19
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 | 54 | 54
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47 |  | 12
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 181.5 | 119.5
Accomplishments |  | Started coding some examples, and have rendered a few items within the browser
Problems |  | will be worrying about getting finished with everything on time.
Changes in Scope, Schedule and Cost |  | Behind Schedule |  | Trying to finish with most of the things I need to learn for my project.
Confessional |  | Actual hours since last update: 10 hours
Total Anticipated actual Hours: 181.5
Finish learning about the basic modal rendering so that I can make my modals.
Scripture |  | Acts 12:18 - Now as soon as [something was rendered], there was no small stir among the [students], what was become of [opengl].

## Status Update 20
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 | 57 | 57
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47 |  | 14
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 181.5 | 124.5
Accomplishments |  | I have been able to render 2d and 3d objects within my browser and been able to capture keyboard input and affect the objects rendered.
Problems |  | My attention is still split between many classes.
Changes in Scope, Schedule and Cost |  | Behind Schedule |  | Still trying to learn things I need to start coding the actual project
Confessional |  | Actual hours since last update: 5 hours
Total Anticipated actual Hours: 181.5
Finish learning about the basic model rendering so that I can make my models.
Scripture |  | Mosiah 3:1 - And again my brethren, I would call [my own] attention, for I have somewhat more to [learn before building]; for behold, I have things to [code] concerning that which is to come.

## Status Update 21
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 | 58 | 58
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47 |  | 14
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 181.5 | 125.5
Accomplishments |  | Changed my classes so that I will finish senior project next semester, but will do a little bit more on the project. Spent time learning about shaders.
Problems |  | Will be doing my senior project remotely next semester, and have to extend a semester.
Changes in Scope, Schedule and Cost |  | Behind Schedule
Confessional |  | Actual hours since last update: 1 hours
Total Anticipated actual Hours: 181.5
Want to make sure I understand just a bit more about shadows and make sure my requirements fit my understanding.
Scripture |  | Job 3:4 – Let that [the senior project] be darkness; let not God regard it from above, neither let the light shine upon it.

## Status Update 22
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 | 63 | 63
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47 |  | 14
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 181.5 | 130.5
Accomplishments |  | Worked on learning how to organize the project to make coding easier. Looked at shadows a bit more, and controls.
Problems |  | Still haven't found a house to move into after the semester is over.
Changes in Scope, Schedule and Cost |  | On schedule |  | Will change my schedule to reflect this this week.
Confessional |  | Actual hours since last update: 5 hours
Total Anticipated actual Hours: 181.5
Need to finish changing my schedule to reflect my actual timeline.
Scripture |  | Abraham 4:14 - And [James] organized the lights in the expanse of the [virtual] heaven, and caused them to divide the day from the night;

## Status Update 23
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 | 68 | 68
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47 |  | 14
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 181.5 | 135.5
Accomplishments |  | Put a texture on a cube.
Problems |  | Having a little trouble with multiple controls at once
Changes in Scope, Schedule and Cost |  | On schedule |  | Finishing my hours this semester
Confessional |  | Actual hours since last update: 5 hours
Total Anticipated actual Hours: 181.5
Will get more time next semester to focus on Senior Project (yes you can laugh).
Scripture |  | D&C 4:5 - …with an eye single to the [Senior Project], [may just] qualify him [to pass].

## Status Update 24
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 | 68 | 68
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47 |  | 14
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 208 | 135.5
Accomplishments |  | Finished the last of my cit 225 labs
Problems |  | Was worried about all of my other assignments and didn't get anything done this week.
Changes in Scope, Schedule and Cost |  | On schedule |  | Finishing my hours this semester
Confessional |  | Actual hours since last update: 0 hours
Total Anticipated actual Hours: 208
Will get more time next semester to focus on Senior Project (yes you can laugh).
Scripture |  | 1 Kings 20:40 – And as thy servant was busy here and there, he was gone. And the king of Israel said unto him, So shall thy judgment be; thyself hast decided it.

## Status Update 25
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 | 71 | 71
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47 |  | 14
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 208 | 138.5
Accomplishments |  | achieved advanced movement on my camo cube (advanced movement is being able to rotate on multiple axis.)
Problems |  | I have to move between this weekend and next.
Changes in Scope, Schedule and Cost |  | On schedule |  | I have finished my hours for this semester
Confessional |  | Actual hours since last update: 3 hours
Total Anticipated actual Hours: 208
Will get more time next semester to focus on Senior Project (yes you can laugh).
Scripture |  | Mosiah 18:32 - But behold, it came to pass that the [student], having discovered a movement among [his project], [was excited because he had been working on it for a while].

## Status Update 26
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 | 76 | 76
Code | not started | 2015-01-20 |  |  | 2015-02-25 |  |  | 47 |  | 14
Test | not started | 2015-03-05 |  |  | 2015-03-25 |  |  | 20
Total Hours | [7 empty] | 189 | 208 | 143.5
Accomplishments |  | Achieved movement, the ability to change the ambient lighting color, and the ability to change the direction the lighting is coming from.
Problems |  | Still have quite a bit of design to go
Changes in Scope, Schedule and Cost |  | On schedule |  | Going to have most of my research/design if not all finished 2 weeks from now, and start on coding the actual project.
Confessional |  | Actual hours since last update: 4 hours
Total Anticipated actual Hours: 208
Things are progressing well so far.
Scripture |  | Alma 43:7 - ...that he might bring [webgl] into subjection to the accomplishment of his designs.