## Sheet1
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 41 | 41
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 | 86.5 | 104.5
Code | not started | 2015-01-20 |  |  | 2015-02-25 | 2015-07-01 |  | 47 | 111 | 111
Test | not started | 2015-03-05 |  |  | 2015-03-25 | 2015-07-29 |  | 20 | 0 | 15
Total Hours | [7 empty] | 189 | 284.5 | 284.5
Accomplishments |  | Finished the project by making shadows directly below each object, and getting approval to change my requirements to only render shadows directly below each object.
Problems |  | None anymore to do with this project.
Changes in Scope, Schedule and Cost |  | On Schedule |  | Finished the Project
Confessional |  | Actual hours since last update: 1.5 hours
Total Anticipated actual Hours: 284.5
Finished the Project.
Scripture |  | Exodus 39:43 - And [Twitchell] did look upon all the work, and, behold, [James] had done it as the [he] had [required of himself], even so had they done it: and [Twitchell said: “You shall not pass”].