## Sheet1
| Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours
|  | Proposed | Mod | Actual | Proposed | Mod | Actual | Proposed | Mod | Actual
Project Selection | finished | 2014-03-01 | 2014-03-01 | 2014-03-01 | 2014-05-06 | 2014-05-07 | 2014-05-07 | 5 | 6 | 6
Prelim | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 3 | 3 | 3
Proposal | finished | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-09 | 2014-05-09 | 2014-05-13 | 4 | 4 | 4
Research/ Requirements | finished | 2014-05-14 | 2014-03-15 | 2014-03-15 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 60 | 40.5 | 40.5
Research/ Design | in progress | 2014-06-20 | 2014-07-10 |  | 2014-07-25 | 2014-09-25 |  | 50 | 86.5 | 104.5
Code | not started | 2015-01-20 |  |  | 2015-02-25 | 2015-07-01 |  | 47 | 60 | 110
Test | not started | 2015-03-05 |  |  | 2015-03-25 | 2015-07-29 |  | 20 | 0 | 15
Total Hours | [7 empty] | 189 | 258 | 283
Accomplishments |  | Made models, animation, and sounds. (this is a bit vague, but Ifinished all shall requirements to models animation, and sounds took several days off work to finish up as much as I could.)
Problems |  | Cannot seem to make shadows.
Changes in Scope, Schedule and Cost |  | Behind Schedule |  | Still researching and coding the shadows.
Confessional |  | Actual hours since last update: 68 hours
Total Anticipated actual Hours: 300
just putting my all into solutions for shadows
Scripture |  | Alma 2:33 - But [the shadows] , contended with the [James] the king of the [Senior Project] until he slew and drove [James] back.